

**TIMELINE FOLLOW-UP**

|  |  |  |
| --- | --- | --- |
| **MONTH** | **ACTIVITY** | **COMMENTS** |
| **SEPT-OCT/18** | Presentation of the project to school | Done |
| Presentation of the project to families | Done |
| Presentation of the project to students | Done |
| Selection of the teachers lead team | Done |
| Selection of the students lead team | Done |
| **OCT/18** | Local logo contest | Done |
| International logo contest | In November (done) |
| **NOV/18** | Surveys among students | Done |
| Surveys among teachers | Not done and we think we do not need them. |
| Discussion about the results of the surveys | Done in LTTA Poland. |
| **DEC/18** | Transmition of the material of teachers’ training course in Fundació Alicia to each school | Done, transmition among lead team of students and teachers. |
| **DEC/18** | Creation of workshops by students | Done |
| Selection of the best workshops in each partner school | Done |
| **DEC/18** | First Healthy Breakfast «DRESSED FRUITS» | Done |
| Creation of leaflets for the 1st breakfast | Done |
| **JAN/19** | Creation of Healthy posters denying false common ideas about nutrition. | Done |
| Poster exhibition in each partner school | Not in all schools so we will do an exhibition of international posters (done) |
| International poster contest | Done |
| **APR/19** | Workshops selected in LTTA takes place in each partner school | Done |
| Workshops selected in LTTA takes place in nearest schools of partner schools | Done except Portugal, Poland and Latvia. Octobre 2019 done everywhere. |
| **APR/19** | 2nd Healthy breakfast «RUN OUT OF SUGAR» | Done |
| Creation of leaflets for the 2nd breakfast | Done |
| **MAY/19** | Teachers write down the workshops lesson plan. | Done |
| **MAY/19** | Creation of the first magazine | Half done in Croatia. FINISHED IN EACH COUNTRY. (done) |
| Translation of the magazine to local languages | Done |
| Delivery of magazines to families | Done |
| **JUN/19** | Dissemination day for families | Done in Catalonia, Portugal, Latvia and Poland. In Croatia it will take place at the end of October. (done) |
| 3rd Healthy breakfast «BREAKFASTS AROUND THE WORLD» | Now postpone to 8th October. Done |
| **JUL/19** | Teachers’ evaluation of the first year. | Done |
| **SEPT/19** | Creation of a multilingual dictionary | It will be done from 22/10 to 22/11. Done in December. |
| **SEPT/19** | Plantation of seeds | Done everywhere except in Catalonia. Done in January. |
| **OCT/19** | Writing of healthy breakfasts recipes | LTTA Portugal |
| Healthy breakfasts videos | Postponed to December – January (youtube channel). Done |
| **DEC/19** | Creation of the second magazine | Postponed to LTTA in Granollers. (done) |
| Translation of the magazine to local languages | **We think this is not necessary because we are going to use them in English classes for the youngest students.** |
| Delivery of magazines to families | Done after Granollers meeting. |
| **JAN/20** | 4th Healthy breakfast | All partners did except Catalonia, they are doing at the end of February. |
| Creation of leaflets for the 4th breakfast | Done |
| **FEB/20** | Public campaign to disseminate the recipe-blog and youtube channel | Done except Croatia. |
| **MAR/20** | Creation of video advertisements | Done in October 2020 due to Covid lockdown |
| **APR/20** | Creation of the third magazine  Creation of a small book with recipes of the project | Done in virtual LTTA by students (tales) |
| Translation of the magazine to local languages | It’s not necessary, we are not going to do that. We will use the magazine for English lessons in our schools. |
| Delivery of magazines to families | Virtualy due to COVID. |
| **MAY/20** | Survey among students and families regarding the impact of the project | We decided to do it to tachers and students in our virtual meeting. |
| **JUN/20** | 5th Healthy breakfast «OUR OWN RECIPES» | Croatian and Latvia did it in the school and the other teams disseminate it on the web. |
| Creation of leaflets for the 5th breakfast | Done. |
| **JUL/20** | Final evaluation of the project made by teachers | Done in virtual meeting. |